## Start Here
O2C POST-IMPLEMENTATION CHECKLIST
LS Financial Management Group ¦ 250+ Items ¦ 10 Categories ¦ Fully Editable
www.lsfinancialmanagement.com ¦ lsfinancialmanage@outlook.com
COMPANY SETUP
Company Name |  | e.g. Acme Corp
O2C Software Platform |  | e.g. HighRadius, Billtrust, Esker
Go-Live Date |  | Enter date (MM/DD/YYYY)
Days Since Go-Live | 2026-06-08 | Auto-calculated
Assessment Date |  | Auto-calculated (today)
Assessment Lead |  | Name of person leading assessment
Executive Sponsor |  | Name of executive sponsor
AR Team Size |  | Number of AR staff
ERP System |  | e.g. SAP, Oracle, NetSuite
IMPLEMENTATION PHASE INDICATOR
Current Phase: | Enter Go-Live Date above
COLOR & PRIORITY LEGEND
CRITICAL | Active gap causing measurable financial impact. Address immediately.
HIGH | Significant gap or risk. Address within 30 days.
STANDARD | Optimization opportunity. Address within 60-90 days.
ONGOING | Continuous monitoring and improvement activity.
STATUS DROPDOWN OPTIONS
Resolved | All actions complete, gap closed.
In Progress | Actively being worked on.
At Risk | Resolution at risk of missing target date.
Gap Identified | Gap documented, not yet actioned.
Not Applicable | Item does not apply to this environment.
Under Review | Under evaluation or assessment.
HOW TO USE THIS WORKBOOK
1. Complete the Company Setup section above with your organization details.
2. Navigate to each Category tab (tabs 1-10) to audit gaps in each functional area.
3. Use the Status dropdown (column D) on each sheet to classify each checklist item.
4. Assign an Owner (column E) and Target Resolution Date (column F) for each open gap.
5. Quantify the financial impact of each gap in column G (Annual $ Impact) wherever possible.
6. The Master Dashboard tab tracks overall gap resolution progress across all categories.
7. Sort any category sheet by Status to prioritize — start with all CRITICAL gaps.
8. Use the Gap Financial Summary tab to build your ROI recovery business case for leadership.
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## Master Dashboard
POST-IMPLEMENTATION GAP RESOLUTION DASHBOARD
Company: |  | Platform: |  | Go-Live: 01/00/1900
OVERALL PROGRESS BY CATEGORY
Category | Total Items | Gap Identified | In Progress | At Risk | Resolved | Not Applicable | Under Review | % Resolved | % Closed | Total $ Impact | Phase Priority
1. System Performance & Configuration | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 1 - Hypercare
2. ERP Integration | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 1 - Hypercare
3. Cash Application | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 1 - Hypercare
4. Collections & Dunning | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 2 - Stabilization
5. Dispute & Deduction | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 2 - Stabilization
6. Reporting & Analytics | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 2 - Stabilization
7. User Adoption & Training | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 3 - Optimization
8. Vendor Accountability & Support | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 3 - Optimization
9. AI & Automation Expansion | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 3 - Optimization
10. Strategic Optimization & ROI | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 4 - Transformation
TOTALS | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | All Phases
KEY GAP METRICS
Critical Gaps Outstanding | 10 | Categories with active critical/at-risk gaps
Total Gap Identified Count | 250 | Items needing remediation
Total In Progress | 0 | Items actively being worked
Total At Risk | 0 | Items flagged as at risk
Total Resolved | 0 | Items successfully closed
Overall % Resolved | 0% | Workbook-wide resolution rate
Estimated Annual $ Impact — Open Gaps | 0 | Sum of $ impact for categories with open items
Total Quantified $ Impact (All) | 0 | All 10 categories combined
30 / 60 / 90 / 180 DAY TARGETS
Target Horizon | Focus | Items Due | Items Complete | % On Track | Status
30-Day Target | All CRITICAL priority gaps resolved or in active remediation | 15 |  | 0% | 🔴 Behind
60-Day Target | All HIGH priority gaps resolved or actively In Progress | 102 |  | 0% | 🔴 Behind
90-Day Target | All STANDARD gaps addressed; AI expansion plan active and deployed | 150 |  | 0% | 🔴 Behind
180-Day Target | Full optimization achieved; ROI baseline confirmed; CFO presentation delivered | 250 |  | 0% | 🔴 Behind
KPI COMPARISON — GO-LIVE BASELINE vs. CURRENT vs. TARGET
KPI | At Go-Live Baseline | Current | Target | Gap to Target | $ Impact of Gap | Trend
DSO (Days)
CEI (%)
Cash App Match Rate (%)
% AR Past Due
Dispute Resolution Days
Write-off Rate (%)
Manual Process Hours/Week
AR Staff Satisfaction Score (1-10)
WORKAROUND INVENTORY SUMMARY
Hourly Rate Assumption ($): | 35
Workaround Description | Function Area | Hours/Week | Annual Cost ($) | Resolution Status | Target Resolution Date | Priority
TOTALS |  | 0 | 0
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 1-System Performance
CATEGORY 1 — SYSTEM PERFORMANCE AND CONFIGURATION GAPS (25 Items)
The first 30 days post-go-live reveal every gap between what was configured and what your business actually needs. Document every gap immediately — gaps left undocumented become permanent workarounds.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Audit actual system match rate vs. contracted/demo rate — document variance and notify vendor in writing | Gap Identified
2 | CRITICAL | Identify all functions shown in demo that are NOT active in current production configuration | Gap Identified
3 | CRITICAL | Audit all batch processing cycles — identify functions running overnight that were sold as real-time | Gap Identified
4 | CRITICAL | Document all manual processes rebuilt by AR team since go-live — this is the workaround inventory | Gap Identified
5 | CRITICAL | Compare go-live date to contractual commitment — if delayed, calculate penalty credits owed and invoice vendor | Gap Identified
6 | HIGH | Audit all dunning communications — are emails sending from correct address, arriving in customer inboxes, and logging responses automatically? | Gap Identified
7 | HIGH | Audit cash application match rate for each payment type: ACH, check, wire, credit card — identify lowest-performing type | Gap Identified
8 | HIGH | Audit collections worklist — is it generating daily? Are priority scores aligned with actual risk? Is it integrated with live AR aging? | Gap Identified
9 | HIGH | Audit dispute routing — are disputes automatically classified and routed, or falling into a manual queue? | Gap Identified
10 | HIGH | Audit credit management module — are credit holds triggering correctly, releasing correctly, and logging all approvals? | Gap Identified
11 | HIGH | Audit customer portal (if applicable) — adoption rate, payment success rate, dispute submission rate | Gap Identified
12 | HIGH | Audit ERP write-back — are all transactions posted back to ERP automatically or requiring manual intervention? | Gap Identified
13 | HIGH | Identify all error messages or system exceptions occurring more than once per week — log and escalate to vendor | Gap Identified
14 | HIGH | Audit reporting module — are all contracted reports available, accurate, and running on schedule? | Gap Identified
15 | HIGH | Test system performance under month-end volume — does system degrade or fail during peak transaction periods? | Gap Identified
16 | STANDARD | Audit user access — are all active users properly provisioned with correct roles and permissions? | Gap Identified
17 | STANDARD | Audit audit trail — is every system action logged with user ID, timestamp, and before/after values? | Gap Identified
18 | STANDARD | Verify SSO and authentication is working correctly for all user types | Gap Identified
19 | STANDARD | Test all email notification templates — are sender addresses, reply-to addresses, and content correct? | Gap Identified
20 | STANDARD | Audit all scheduled jobs and automated workflows — confirm all are running on schedule with no silent failures | Gap Identified
21 | STANDARD | Verify all customer master data loaded correctly — compare sample of 50 accounts to ERP source | Gap Identified
22 | STANDARD | Audit all payment terms configurations — confirm terms in system match ERP and contracts | Gap Identified
23 | STANDARD | Test all system integrations with live data — confirm no data loss, duplication, or transformation errors | Gap Identified
24 | STANDARD | Verify all custom reports are producing accurate results — validate against ERP source data | Gap Identified
25 | ONGOING | Monitor system uptime and performance weekly — track against SLA commitments in contract | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 2-ERP Integration
CATEGORY 2 — ERP INTEGRATION GAPS (25 Items)
ERP integration gaps are the most common and most expensive post-go-live discovery. Every gap between the O2C software and your ERP creates a manual workaround that must be identified, quantified, and resolved.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Audit real-time vs. batch data flow between O2C software and ERP — document every integration that runs on batch when real-time was contracted | Gap Identified
2 | CRITICAL | Identify all data fields present in ERP that are NOT flowing to O2C software — document each missing field and its operational impact | Gap Identified
3 | CRITICAL | Identify all O2C software outputs that are NOT posting back to ERP automatically — these are manual re-keying workarounds | Gap Identified
4 | CRITICAL | Test credit hold status synchronization: when O2C applies a credit hold, does ERP block new orders within contracted timeframe? | Gap Identified
5 | CRITICAL | Test payment posting: when O2C applies a payment, does ERP sub-ledger and GL update automatically and correctly? | Gap Identified
6 | HIGH | Audit AR aging data synchronization: is the AR aging in O2C software matching the ERP AR aging within acceptable tolerance? | Gap Identified
7 | HIGH | Audit customer master synchronization: when new customers or changes are made in ERP, do they flow to O2C software correctly and within what timeframe? | Gap Identified
8 | HIGH | Audit invoice data flow: are all invoice fields (number, amount, date, terms, line items) flowing correctly and completely? | Gap Identified
9 | HIGH | Audit payment remittance data: are all remittance details (invoice references, discount amounts, deduction codes) flowing correctly? | Gap Identified
10 | HIGH | Test deduction and dispute write-back: when disputes are resolved in O2C software, does the resolution post correctly to ERP? | Gap Identified
11 | HIGH | Audit EDI transaction handling: are all EDI 820 payment remittances processing correctly through the integration? | Gap Identified
12 | HIGH | Test multi-currency transaction handling if applicable: are exchange rates applying correctly at both O2C and ERP levels? | Gap Identified
13 | HIGH | Audit integration error handling: when integration fails, is an alert generated, is the error logged, and is there a retry mechanism? | Gap Identified
14 | HIGH | Test integration performance at peak volume: does integration maintain latency within acceptable thresholds during month-end? | Gap Identified
15 | HIGH | Document all integration middleware (iPaaS, RPA, custom scripts) — assess stability and maintenance risk of each | Gap Identified
16 | STANDARD | Evaluate MCP (Model Context Protocol) readiness for SAP/Oracle/NetSuite — can AI be connected directly to ERP via MCP to eliminate current integration gaps? | Gap Identified
17 | STANDARD | Audit all custom API endpoints built during implementation — document, test, and assign ownership for maintenance | Gap Identified
18 | STANDARD | Verify all RPA bots (if in use) are running reliably — document each bot, its trigger, its failure rate, and its maintenance owner | Gap Identified
19 | STANDARD | Test integration failover and recovery — what happens when the integration connection drops? Is there an automatic recovery? | Gap Identified
20 | STANDARD | Audit integration monitoring and alerting — is someone notified within 15 minutes if an integration fails? | Gap Identified
21 | STANDARD | Evaluate Power Automate or iPaaS alternatives to current brittle integrations — identify upgrade path | Gap Identified
22 | STANDARD | Document all data transformation rules applied in the integration layer — are they documented and version-controlled? | Gap Identified
23 | STANDARD | Verify all integration logs are retained for minimum 90 days for audit purposes | Gap Identified
24 | STANDARD | Assess ERP upgrade compatibility: what happens to integrations when ERP updates? Is there a test protocol? | Gap Identified
25 | ONGOING | Review integration performance metrics monthly — latency, failure rate, volume, error rate — trend analysis | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 3-Cash Application
CATEGORY 3 — CASH APPLICATION GAPS (25 Items)
Cash application gaps are directly measurable in dollars and hours. Every percentage point of unmatched cash costs your team time and your business carrying costs. Quantify every gap.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Measure current auto-match rate for each payment type — compare to contracted rate and demo rate — document variance | Gap Identified
2 | CRITICAL | Quantify volume and $ value of payments in manual review queue daily — this is the true cost of the gap | Gap Identified
3 | CRITICAL | Identify top 5 reasons for cash application failures — create a root cause log with count and $ value for each | Gap Identified
4 | CRITICAL | Audit unapplied cash balance — calculate carrying cost at cost of capital — escalate if above acceptable threshold | Gap Identified
5 | CRITICAL | Test remittance processing for each format: EDI 820, bank file, email PDF, portal notification — identify format with lowest match rate | Gap Identified
6 | HIGH | Audit same-day application rate — what percentage of payments received today are applied today? | Gap Identified
7 | HIGH | Audit short-payment handling — are short payments auto-flagged correctly? Is tolerance level configured correctly? | Gap Identified
8 | HIGH | Audit overpayment handling — are overpayments auto-creating credits correctly in ERP? | Gap Identified
9 | HIGH | Audit multi-invoice payment handling — are payments that cover multiple invoices matched correctly? | Gap Identified
10 | HIGH | Test parent-child account hierarchy handling — are payments from subsidiaries applying to the correct parent account? | Gap Identified
11 | HIGH | Audit discount handling — are early payment discounts being validated against contract terms before applying? | Gap Identified
12 | HIGH | Identify AI vs. OCR vs. rules-based matching performance difference — which technology is driving highest match rates? | Gap Identified
13 | HIGH | Measure AI model training progress — is match rate improving month-over-month as model trains on your data? | Gap Identified
14 | HIGH | Audit exception queue management — how long do unmatched items sit in queue before manual intervention? What is the SLA? | Gap Identified
15 | HIGH | Test lockbox file processing — are lockbox files from your bank processing correctly and completely? | Gap Identified
16 | STANDARD | Evaluate ChatGPT or AI prompt workflow to supplement low match rate payment types — calculate potential improvement | Gap Identified
17 | STANDARD | Audit write-off processing in cash application — are small balance write-offs processing correctly with proper GL coding? | Gap Identified
18 | STANDARD | Audit intercompany payment handling if applicable | Gap Identified
19 | STANDARD | Evaluate MCP integration to connect bank remittance data directly to AI matching — assess feasibility and ROI | Gap Identified
20 | STANDARD | Measure staff hours per week spent on manual cash application — calculate annual cost of current manual work | Gap Identified
21 | STANDARD | Benchmark match rate against industry standard (85-90% target) — document gap and create improvement plan | Gap Identified
22 | STANDARD | Audit deduction coding at cash application — are deduction reason codes being assigned correctly at point of application? | Gap Identified
23 | STANDARD | Test foreign currency cash application if applicable — are exchange rate calculations correct? | Gap Identified
24 | STANDARD | Review and update cash application matching rules monthly — ensure rules align with current customer payment behavior | Gap Identified
25 | ONGOING | Track cash application KPIs weekly: match rate by type, unapplied balance, exception volume, days to apply — trend analysis | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 4-Collections & Dunning
CATEGORY 4 — COLLECTIONS AND DUNNING GAPS (25 Items)
Collections gaps directly impact DSO, CEI, and cash flow. Every gap is measurable. Every workaround your collectors rebuilt post-go-live represents a system failure that must be addressed.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Audit dunning automation completeness — is every overdue account receiving automated outreach or are gaps in coverage allowing accounts to age silently? | Gap Identified
2 | CRITICAL | Audit collections worklist accuracy — does the worklist reflect real-time AR aging from ERP or is it running on stale data? | Gap Identified
3 | CRITICAL | Audit dunning priority scoring — are high-balance, high-risk accounts appearing at the top of the worklist every morning? | Gap Identified
4 | CRITICAL | Identify all accounts that have aged past 60 days with zero collector contact logged in the system — these are coverage gaps | Gap Identified
5 | CRITICAL | Measure and document current DSO vs. pre-go-live DSO baseline — quantify the impact of implementation on cash flow | Gap Identified
6 | HIGH | Audit dunning email deliverability — are emails landing in customer inboxes or being flagged as spam? Test with key customer domains | Gap Identified
7 | HIGH | Audit dunning template effectiveness — are dunning emails generating responses and payments or being ignored? Track open rates and response rates | Gap Identified
8 | HIGH | Audit promise-to-pay tracking — when customers make payment promises, are they being logged and auto-followed-up when broken? | Gap Identified
9 | HIGH | Audit contact rate by collector — how many outbound contacts per collector per day? What is the benchmark vs. target? | Gap Identified
10 | HIGH | Audit escalation workflow — when a collector escalates an account, does it route correctly to the next tier with full history attached? | Gap Identified
11 | HIGH | Audit credit hold trigger integration — when an account hits credit limit in O2C, does ERP automatically block new orders? | Gap Identified
12 | HIGH | Audit dispute-to-collections handoff — when a dispute is identified during collections, does it route correctly to the dispute team? | Gap Identified
13 | HIGH | Measure collector productivity per FTE — invoices contacted, $ collected, promises obtained — compare to pre-implementation baseline | Gap Identified
14 | HIGH | Audit automated follow-up on broken promises — does the system auto-escalate when a promise-to-pay date passes without payment? | Gap Identified
15 | HIGH | Test collections system integration with real-time ERP AR data — confirm that payments post in ERP and update collector worklist same-day | Gap Identified
16 | STANDARD | Deploy AI dunning prompt pack to supplement automated dunning for accounts with complex dispute history or relationship-sensitive situations | Gap Identified
17 | STANDARD | Evaluate AI-powered collections prioritization — can ChatGPT or Copilot analyze aging data and recommend daily call priority order? | Gap Identified
18 | STANDARD | Audit CEI (Collections Effectiveness Index) trending — is CEI improving, flat, or declining since go-live? | Gap Identified
19 | STANDARD | Audit customer-specific dunning rules — are VIP or strategic accounts receiving customized communication cadences? | Gap Identified
20 | STANDARD | Audit multi-currency collections workflow if applicable — are foreign currency invoices being collected with correct local context? | Gap Identified
21 | STANDARD | Audit collections team reporting — does each collector have a daily scorecard showing their portfolio performance? | Gap Identified
22 | STANDARD | Audit collector notes quality — are collectors documenting call outcomes, promises, and next steps in the system or in personal spreadsheets? | Gap Identified
23 | STANDARD | Evaluate AI-assisted dispute drafting for collectors — can AI draft initial dispute acknowledgment emails to reduce manual writing time? | Gap Identified
24 | STANDARD | Benchmark dunning sequence timing against industry best practice — are the days-past-due intervals for each dunning level optimized? | Gap Identified
25 | ONGOING | Track collections KPIs weekly: DSO trend, CEI trend, promise-to-pay kept rate, collector productivity, broken promise rate — executive dashboard | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 5-Dispute & Deduction
CATEGORY 5 — DISPUTE AND DEDUCTION GAPS (25 Items)
Unresolved disputes age into write-offs. Every day a dispute sits unresolved costs carrying cost and risks permanent loss. Audit every dispute process for gaps.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Audit dispute intake automation — are all customer disputes being captured in the system, or are some arriving via email and never logged? | Gap Identified
2 | CRITICAL | Audit dispute classification accuracy — are dispute reason codes being assigned correctly at intake? Incorrect codes corrupt root cause data | Gap Identified
3 | CRITICAL | Audit dispute routing accuracy — are disputes automatically routing to the correct internal owner (AR, Sales, Operations, Logistics) based on reason code? | Gap Identified
4 | CRITICAL | Measure current average dispute resolution days vs. pre-go-live baseline and vs. contracted SLA target | Gap Identified
5 | CRITICAL | Audit disputes aged over 90 days — calculate total open dollar value and carrying cost — escalate all to senior management immediately | Gap Identified
6 | HIGH | Audit documentation request automation — when a dispute requires proof of delivery or invoice copy, does the system auto-request from the right internal team? | Gap Identified
7 | HIGH | Audit internal escalation workflow — when a dispute exceeds SLA, does it auto-escalate to manager with full dispute history attached? | Gap Identified
8 | HIGH | Audit vendor-side dispute response SLAs — are you tracking how long the O2C software vendor takes to resolve disputes that are system configuration issues? | Gap Identified
9 | HIGH | Audit deduction reason code library — is the reason code list complete, current, and aligned with actual deduction types your customers are taking? | Gap Identified
10 | HIGH | Audit deduction root cause trending — which deduction types are recurring? Are root causes being fed back to Sales, Operations, or Logistics? | Gap Identified
11 | HIGH | Audit write-off approval workflow — are write-offs requiring proper dual approval and GL coding before posting? Is the audit trail complete? | Gap Identified
12 | HIGH | Audit recovery rate by dispute type — what percentage of disputed amounts are being recovered vs. written off by reason code? | Gap Identified
13 | HIGH | Audit customer communication automation for disputes — are customers receiving automatic status updates as their dispute moves through the workflow? | Gap Identified
14 | HIGH | Test dispute aging report accuracy — does the dispute aging report in O2C match the dispute balances in ERP AR? | Gap Identified
15 | HIGH | Audit pre-deduction notification handling — when customers send advance deduction notices (chargebacks), are they being captured and processed before the payment arrives? | Gap Identified
16 | STANDARD | Deploy AI dispute drafting workflow — use ChatGPT or Copilot to draft dispute denial letters, credit memo requests, and customer resolution communications | Gap Identified
17 | STANDARD | Evaluate AI-powered dispute classification — can AI analyze incoming dispute text and auto-assign the most accurate reason code? | Gap Identified
18 | STANDARD | Audit short-payment dispute threshold — is the auto-write-off tolerance level set correctly? Are you writing off disputes that should be collected? | Gap Identified
19 | STANDARD | Build dispute resolution time target tracking: 30-day target for CRITICAL disputes, 60-day for HIGH, 90-day for STANDARD — measure compliance | Gap Identified
20 | STANDARD | Audit intercompany dispute handling if applicable — are internal disputes between subsidiaries being processed through the same workflow? | Gap Identified
21 | STANDARD | Evaluate MCP integration to pull dispute-related ERP data (PO, receipt, invoice) directly into AI for faster resolution recommendation | Gap Identified
22 | STANDARD | Audit dispute dashboard for executive visibility — can your CFO see open dispute aging, recovery rates, and trend in real time? | Gap Identified
23 | STANDARD | Measure dispute team productivity per FTE — disputes opened, disputes resolved, $ recovered, average resolution days | Gap Identified
24 | STANDARD | Audit recurring deduction management — are high-frequency, low-dollar deductions from the same customers being batched for efficient processing? | Gap Identified
25 | ONGOING | Track dispute KPIs monthly: open dispute balance, average resolution days, recovery rate by type, write-off rate, root cause trend — CFO-level reporting | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 6-Reporting & Analytics
CATEGORY 6 — REPORTING AND ANALYTICS GAPS (25 Items)
If your CFO is still getting AR reports from an Excel file someone builds manually every week, the reporting module is not delivering its value. Audit every reporting gap.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Audit availability of all contracted standard reports — are all reports that were contracted and demonstrated now available in production? | Gap Identified
2 | CRITICAL | Audit AR aging report accuracy — does the AR aging report in O2C software match the AR aging in ERP sub-ledger to the dollar? | Gap Identified
3 | CRITICAL | Identify all manual Excel reports still being built by AR staff each week — each one represents a reporting module gap | Gap Identified
4 | CRITICAL | Audit CFO/executive reporting package — is the CFO receiving automated AR performance reports or still relying on manually prepared summaries? | Gap Identified
5 | HIGH | Audit DSO trending report — is DSO tracked daily/weekly/monthly with comparison to prior periods and go-live baseline? | Gap Identified
6 | HIGH | Audit CEI trending report — is CEI calculated correctly and trending in the right direction since go-live? | Gap Identified
7 | HIGH | Audit cash application performance report — does it show match rate by payment type, exception volume, and trend over time? | Gap Identified
8 | HIGH | Audit collector productivity scorecard — does each collector see their own daily performance metrics in the system? | Gap Identified
9 | HIGH | Audit dispute aging report — does it segment by reason code, aging bucket, dollar value, and responsible owner? | Gap Identified
10 | HIGH | Audit executive KPI dashboard — are all key AR metrics visible in a single real-time dashboard accessible to senior leadership? | Gap Identified
11 | HIGH | Audit custom dashboard configuration — were all custom dashboards from the implementation spec actually built and validated with end users? | Gap Identified
12 | HIGH | Audit real-time vs. scheduled report delivery — which reports require manual refresh? Which should be real-time but are not? | Gap Identified
13 | HIGH | Test report subscription and distribution — are weekly/monthly reports automatically emailing to the correct recipients on schedule? | Gap Identified
14 | HIGH | Audit report drill-down functionality — can users click from summary to detail to invoice level in contracted reports? | Gap Identified
15 | HIGH | Audit Power BI or Tableau integration if applicable — is the O2C data feeding correctly into enterprise BI tools? | Gap Identified
16 | STANDARD | Deploy AI-powered weekly AR analysis workflow — use ChatGPT or Copilot prompt to analyze AR aging export and generate executive commentary automatically | Gap Identified
17 | STANDARD | Evaluate AI-generated KPI narrative — can AI draft the written explanation of weekly AR performance for the CFO report? | Gap Identified
18 | STANDARD | Audit month-end reporting package — does the system auto-generate all month-end AR close reports or does the team still manually compile? | Gap Identified
19 | STANDARD | Audit write-off trending report — is write-off rate tracked by reason code, customer, and business unit with trend comparison? | Gap Identified
20 | STANDARD | Audit credit management reporting — are credit limit utilization, credit hold status, and credit review aging visible in real-time? | Gap Identified
21 | STANDARD | Audit customer portal activity reporting if applicable — are portal login rates, payment submission rates, and dispute submission rates tracked? | Gap Identified
22 | STANDARD | Evaluate self-service reporting for business stakeholders — can Sales, Operations, and Finance access AR data relevant to their function without AR team involvement? | Gap Identified
23 | STANDARD | Audit report access controls — are reports containing sensitive customer data restricted to appropriate user roles? | Gap Identified
24 | STANDARD | Benchmark reporting module against implementation spec — document every report that was contracted but not delivered | Gap Identified
25 | ONGOING | Publish weekly AR performance dashboard to executive team every Monday — track trend lines for DSO, CEI, match rate, dispute balance, and write-off rate | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 7-User Adoption
CATEGORY 7 — USER ADOPTION AND TRAINING GAPS (25 Items)
The single most reliable sign that an O2C implementation is underperforming is an AR team that rebuilt their old processes alongside the new system. Adoption gaps are measurable and fixable.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Measure system login frequency by user — identify users logging in less than 3x per week as adoption risk requiring immediate intervention | Gap Identified
2 | CRITICAL | Identify all manual workarounds built alongside the system — for each workaround, determine if it replaces a system function or fills a true gap | Gap Identified
3 | CRITICAL | Audit feature utilization rate by module — which contracted modules have zero or near-zero active user engagement? | Gap Identified
4 | CRITICAL | Conduct user satisfaction survey — NPS score across all AR users — benchmark and track quarterly | Gap Identified
5 | HIGH | Audit role-specific training completion — has every user completed training for their specific role and the modules they are responsible for? | Gap Identified
6 | HIGH | Audit super-user effectiveness — are designated super-users able to answer peer questions and resolve basic configuration issues without vendor support? | Gap Identified
7 | HIGH | Audit manager adoption of reporting tools — are AR managers and team leads using system dashboards or reverting to manual Excel tracking? | Gap Identified
8 | HIGH | Audit executive adoption of dashboards — are the CFO and VP of Finance accessing the executive dashboard, or is AR staff still preparing manual briefings? | Gap Identified
9 | HIGH | Audit new hire training program — when a new AR team member joins, is there a structured onboarding path in the O2C system or is training ad hoc? | Gap Identified
10 | HIGH | Audit help documentation availability — are system help guides, process SOPs, and training materials accessible inside the system or on a shared drive? | Gap Identified
11 | HIGH | Measure user confidence score by module — do users feel confident using each module, or are they uncertain and defaulting to old processes? | Gap Identified
12 | HIGH | Audit process compliance — are all users following the designed O2C workflow from invoice to payment, or are there unauthorized process bypasses? | Gap Identified
13 | HIGH | Identify power users by module — the top 20% of users generating 80% of system activity — leverage them as internal champions | Gap Identified
14 | HIGH | Audit resistance sources — which team members or roles are actively resisting adoption? What are their objections? Address each formally | Gap Identified
15 | HIGH | Audit Collections team daily workflow — does each collector start their day with the system worklist or with a personal spreadsheet? | Gap Identified
16 | STANDARD | Deploy AI workflow training for all AR staff — ensure each team member can use at least one AI prompt workflow to supplement their daily tasks | Gap Identified
17 | STANDARD | Evaluate gamification of adoption metrics — can productivity scores and adoption rates be shared in a team leaderboard to drive engagement? | Gap Identified
18 | STANDARD | Build and publish monthly system utilization report — show login frequency, feature usage, and workflow compliance by user | Gap Identified
19 | STANDARD | Audit vendor training resources — are all vendor-provided training videos, guides, and certification programs being actively used? | Gap Identified
20 | STANDARD | Evaluate O2C certification program enrollment — has the team been enrolled in any vendor or third-party O2C certification coursework? | Gap Identified
21 | STANDARD | Conduct quarterly user feedback session — structured 30-minute session with each user role group to surface friction points and adoption barriers | Gap Identified
22 | STANDARD | Audit system notification settings per user — are users receiving the right alerts and not experiencing notification fatigue from irrelevant alerts? | Gap Identified
23 | STANDARD | Build a process deviation log — track every instance where a user bypasses the designed workflow — identify patterns for retraining or reconfiguration | Gap Identified
24 | STANDARD | Evaluate change management support — was formal change management deployed during implementation? If not, deploy a lightweight adoption program now | Gap Identified
25 | ONGOING | Track system adoption KPIs monthly: active users, login frequency, feature utilization rate, user satisfaction NPS, workaround count — trend report to leadership | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 8-Vendor Accountability
CATEGORY 8 — VENDOR ACCOUNTABILITY AND SUPPORT (25 Items)
The contract you signed has teeth — but only if you use them. Every SLA breach, every unfulfilled commitment, every pending enhancement is a contractual obligation. Audit and enforce.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Audit all open support tickets — how many are older than 30 days? 60 days? 90 days? Escalate all tickets exceeding SLA in writing to your named account executive | Gap Identified
2 | CRITICAL | Measure SLA compliance rate — what percentage of support tickets were resolved within the contracted SLA timeframe? Document every breach | Gap Identified
3 | CRITICAL | Audit outstanding enhancement requests — which enhancements were committed to at contract signing that have not yet been delivered? Document and demand timeline | Gap Identified
4 | CRITICAL | Identify contractual go-live penalty credits — if go-live was delayed beyond contracted date, calculate credits owed and submit formal invoice to vendor | Gap Identified
5 | CRITICAL | Audit named support contact availability — when you call or email your named support contact, what is the actual average response time vs. contracted SLA? | Gap Identified
6 | HIGH | Audit all open bug reports and system defects — are they being actively worked or sitting in backlog? Demand written status on all items older than 30 days | Gap Identified
7 | HIGH | Review vendor product roadmap — what features are committed for the next 12 months? Get written confirmation that features relevant to your gaps are on the roadmap | Gap Identified
8 | HIGH | Audit escalation effectiveness — when you escalate an issue to vendor management, is it resolved faster? Document escalation contacts and their response patterns | Gap Identified
9 | HIGH | Monitor vendor NPS score and industry reviews — is the vendor receiving poor ratings from other customers? This informs your leverage at renewal | Gap Identified
10 | HIGH | Audit subcontractor changes since go-live — has the vendor changed any implementation partners, integration providers, or hosting infrastructure? Demand notification | Gap Identified
11 | HIGH | Audit security and compliance updates — has the vendor issued any security advisories, patch updates, or compliance certifications since go-live? Are you current? | Gap Identified
12 | HIGH | Test data portability right now — can you export your complete AR data (customers, invoices, payment history, dispute history) in a usable format today? | Gap Identified
13 | HIGH | Schedule Executive Business Review (EBR) — demand a formal quarterly EBR with vendor senior leadership, your performance data, and a gap remediation agenda | Gap Identified
14 | HIGH | Submit formal written gap log to vendor — compile all identified gaps into a single formal document and submit to vendor Account Executive with resolution timeline demands | Gap Identified
15 | HIGH | Audit contract terms for annual rate cap — does your contract cap annual price increases? Verify and document the cap percentage before renewal discussions begin | Gap Identified
16 | STANDARD | Audit vendor community and user group participation — are you connected to the vendor's customer community to learn workarounds and influence roadmap? | Gap Identified
17 | STANDARD | Benchmark your support ticket volume and type against similar customers — are you generating more tickets than average? This may indicate a configuration gap | Gap Identified
18 | STANDARD | Audit vendor training resources — are all promised training resources, certifications, and knowledge base articles available to your team? | Gap Identified
19 | STANDARD | Build a formal vendor performance scorecard — score the vendor monthly on support responsiveness, product stability, roadmap delivery, and customer success quality | Gap Identified
20 | STANDARD | Evaluate vendor financial stability — has the vendor had any ownership changes, layoffs, or funding events since contract signing that affect service continuity? | Gap Identified
21 | STANDARD | Audit contract auto-renewal terms — when does your contract auto-renew? What is the notification window to opt out or renegotiate? | Gap Identified
22 | STANDARD | Evaluate competitive alternatives — research 2-3 competing O2C platforms and their current capabilities — maintain competitive intelligence for renewal leverage | Gap Identified
23 | STANDARD | Audit professional services availability — if you need vendor PS resources to close configuration gaps, what is their current availability and rate? | Gap Identified
24 | STANDARD | Document all verbal commitments made by vendor during sales process — compile with emails and meeting notes — these are leverage in remediation discussions | Gap Identified
25 | ONGOING | Maintain a live vendor accountability log — every commitment, every SLA breach, every open item — reviewed monthly with your vendor account team | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 9-AI & Automation
CATEGORY 9 — AI AND AUTOMATION EXPANSION (25 Items)
Your O2C software is the foundation. AI — connected via MCP, APIs, or prompt workflows — is what fills the gaps and delivers the transformation results your team expected at go-live.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Assess MCP (Model Context Protocol) integration feasibility for your ERP — can AI agents connect directly to SAP, Oracle, or NetSuite via MCP to eliminate current O2C integration gaps? | Gap Identified
2 | CRITICAL | Identify the top 3 manual processes in your AR workflow that AI could automate today — rank by hours/week and annual cost — build the business case | Gap Identified
3 | CRITICAL | Deploy ChatGPT or Copilot prompt workflow for cash application gap coverage — AI-assisted remittance matching for the payment types with lowest auto-match rates | Gap Identified
4 | CRITICAL | Deploy AI dunning prompt pack — use AI to draft personalized, context-aware collection emails for accounts that do not respond to automated dunning templates | Gap Identified
5 | CRITICAL | Conduct AI readiness assessment — do you have the data access, IT support, governance framework, and staff capability to deploy AI workflows across AR? | Gap Identified
6 | HIGH | Deploy AI collections prioritization workflow — daily prompt that analyzes AR aging, payment history, and dispute status to generate a ranked call priority list for collectors | Gap Identified
7 | HIGH | Deploy AI dispute drafting workflow — AI drafts dispute denial letters, credit memo requests, and customer resolution emails — collector reviews and sends | Gap Identified
8 | HIGH | Deploy AI weekly KPI analysis prompt — weekly prompt that analyzes AR performance data and generates a written executive summary with trend commentary and risk alerts | Gap Identified
9 | HIGH | Deploy AI credit review workflow — AI analyzes customer payment history, aging trend, dispute frequency, and external credit signals to generate a credit recommendation | Gap Identified
10 | HIGH | Evaluate ERP-to-AI connector options — assess API direct connection vs. iPaaS platform vs. MCP vs. RPA for connecting your ERP data to AI workflows — select and implement | Gap Identified
11 | HIGH | Build AI prompt library — create a shared, maintained library of all AI prompts used by AR team — version-controlled, role-specific, with output examples | Gap Identified
12 | HIGH | Establish AI governance framework — define acceptable AI use cases, output review requirements, prohibited uses, and audit trail documentation for all AI-assisted actions | Gap Identified
13 | HIGH | Audit AI output quality — for every AI workflow deployed, sample 10 outputs per week and score for accuracy, tone, and compliance — track trend | Gap Identified
14 | HIGH | Measure AI time savings — for each AI workflow deployed, calculate actual hours saved per week per user — compile into ROI report for leadership | Gap Identified
15 | HIGH | Ensure AI output audit trail — all AI-generated content that is sent externally (emails, letters, portal messages) must be logged with user review confirmation | Gap Identified
16 | STANDARD | Evaluate AI-powered predictive DSO modeling — can AI analyze current AR aging and payment behavior to predict DSO for next 30/60/90 days? | Gap Identified
17 | STANDARD | Evaluate customer payment behavior scoring — can AI analyze payment history by customer to predict likelihood of late payment and flag proactively? | Gap Identified
18 | STANDARD | Evaluate early warning credit alert system — can AI monitor news, public filings, and payment trends to flag customers at elevated credit risk before default? | Gap Identified
19 | STANDARD | Complete staff AI training — every AR team member completes a structured AI prompt writing course and demonstrates competency with at least one AR-specific workflow | Gap Identified
20 | STANDARD | Evaluate Copilot for Microsoft 365 deployment if on Microsoft stack — assess AR-specific use cases (email drafting, data analysis, report generation) and ROI | Gap Identified
21 | STANDARD | Audit vendor AI capabilities — what AI features are on the O2C software roadmap? What is the delivery timeline? Are they redundant with your internal AI deployments? | Gap Identified
22 | STANDARD | Build AI ROI measurement framework — for each AI workflow, define the KPI baseline, track monthly improvement, and report quarterly AI ROI to CFO | Gap Identified
23 | STANDARD | Evaluate AI-powered invoice processing — can AI extract and validate invoice data from unstructured sources (PDF, email, EDI) to reduce manual data entry? | Gap Identified
24 | STANDARD | Assess AI vendor partner ecosystem — which AI vendors and integration partners does your O2C software vendor officially support or certify? | Gap Identified
25 | ONGOING | Review AI workflow performance monthly — accuracy rate, time savings, user adoption, output quality score — update prompt library based on learnings | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## 10-Strategic Optimization
CATEGORY 10 — STRATEGIC OPTIMIZATION AND ROI (25 Items)
At 90-180+ days post-go-live, the implementation phase is over. This is the performance phase. Every item in this category drives measurable financial improvement.
# | Priority | Checklist Item / Gap to Audit | Status | Owner | Target Resolution Date | Annual $ Impact | Notes / Gap Description
1 | CRITICAL | Measure current DSO vs. go-live baseline — calculate the exact improvement or deterioration in DSO since go-live and quantify the cash flow impact | Gap Identified
2 | CRITICAL | Measure current CEI vs. go-live baseline — is Collections Effectiveness Index above or below pre-implementation levels? If below, identify root cause | Gap Identified
3 | CRITICAL | Measure cash application match rate vs. go-live baseline — has auto-match rate improved? Calculate annual labor savings from match rate improvement | Gap Identified
4 | CRITICAL | Calculate quantified ROI vs. original business case — compare actual performance improvement to the projected ROI that justified the software purchase | Gap Identified
5 | CRITICAL | Prepare CFO/board ROI presentation — compile all performance data, gap resolution progress, and financial impact into an executive-grade presentation | Gap Identified
6 | HIGH | Measure write-off rate reduction vs. baseline — has the dispute and collections improvement reduced the write-off rate? Quantify annual recovery improvement | Gap Identified
7 | HIGH | Measure dispute resolution time reduction — average days to resolve a dispute vs. pre-go-live baseline — quantify carrying cost savings | Gap Identified
8 | HIGH | Measure staff productivity improvement — AR FTE output (invoices processed, payments applied, disputes resolved) vs. pre-implementation baseline per FTE | Gap Identified
9 | HIGH | Prepare contract renewal strategy with performance data — use actual KPI improvement data as leverage for rate negotiation and module expansion decisions | Gap Identified
10 | HIGH | Build vendor performance scorecard for renewal negotiation — score vendor on every dimension: support, product delivery, integration quality, roadmap fulfillment | Gap Identified
11 | HIGH | Assess Phase 2 module expansion — now that baseline is established, evaluate additional O2C modules (credit, portal, e-invoicing) for ROI-positive expansion | Gap Identified
12 | HIGH | Develop 12-month O2C transformation roadmap — written plan covering gap remediation, AI expansion, process optimization, and KPI targets for next 12 months | Gap Identified
13 | HIGH | Build annual AR performance benchmark — compare your KPIs to industry benchmarks (DSO, CEI, match rate, dispute rate) — identify where you rank and what top quartile looks like | Gap Identified
14 | HIGH | Assess strategic recommendation: stay, expand, or replace — based on performance data, gap inventory, and vendor accountability audit, make a formal recommendation to leadership | Gap Identified
15 | HIGH | Conduct full workaround elimination sprint — set a 90-day target to eliminate all identified manual workarounds either through system configuration, AI, or process redesign | Gap Identified
16 | STANDARD | Enroll team in O2C certification program — formal AR and O2C certification for key team members establishes professional development and process discipline | Gap Identified
17 | STANDARD | Publish O2C process playbook — document all current-state AR processes in the O2C system, including decision rules, escalation paths, and exception handling | Gap Identified
18 | STANDARD | Evaluate LS Financial Management Group marketplace resources — audit which tools, templates, and prompt packs are available to supplement your current O2C gaps | Gap Identified
19 | STANDARD | Build AR team incentive structure aligned to KPIs — tie team performance rewards to DSO improvement, CEI, match rate, and dispute resolution metrics | Gap Identified
20 | STANDARD | Conduct post-implementation lessons learned session — formal debrief of what worked, what failed, and what the team would do differently — documented for future reference | Gap Identified
21 | STANDARD | Assess customer experience impact — are customers finding it easier or harder to pay, dispute, and communicate since go-live? Survey 10-20 key customers | Gap Identified
22 | STANDARD | Evaluate e-invoicing expansion — are customers requesting electronic invoice delivery through portals or EDI? What is the adoption rate and cost savings opportunity? | Gap Identified
23 | STANDARD | Build O2C center of excellence — designate a small team responsible for ongoing O2C optimization, AI governance, vendor management, and KPI reporting | Gap Identified
24 | STANDARD | Audit data quality improvement — is the customer master, invoice data, and payment data cleaner today than at go-live? Data quality directly drives automation performance | Gap Identified
25 | ONGOING | Publish quarterly O2C performance report to executive leadership — DSO trend, CEI trend, AI ROI, gap resolution progress, and 12-month outlook — executive-grade presentation | Gap Identified
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only

## Gap Financial Summary
GAP FINANCIAL SUMMARY & ROI ANALYSIS
Company: |  | Platform: |  | Go-Live: 01/00/1900 |  | Assessment: 01/00/1900
SECTION 1 — GAP IMPACT BY CATEGORY
Category | Total Items | # Gaps Identified | # Critical Gaps | Quantified Annual $ Impact | Est. Resolution Cost | Net Annual Benefit | Priority Phase
1. System Performance | 25 | 25 | 5 | 0 |  | 0 | 1-Hypercare
2. ERP Integration | 25 | 25 | 5 | 0 |  | 0 | 1-Hypercare
3. Cash Application | 25 | 25 | 5 | 0 |  | 0 | 1-Hypercare
4. Collections & Dunning | 25 | 25 | 5 | 0 |  | 0 | 2-Stabilization
5. Dispute & Deduction | 25 | 25 | 5 | 0 |  | 0 | 2-Stabilization
6. Reporting & Analytics | 25 | 25 | 4 | 0 |  | 0 | 2-Stabilization
7. User Adoption & Training | 25 | 25 | 4 | 0 |  | 0 | 3-Optimization
8. Vendor Accountability | 25 | 25 | 5 | 0 |  | 0 | 3-Optimization
9. AI & Automation | 25 | 25 | 5 | 0 |  | 0 | 3-Optimization
10. Strategic Optimization | 25 | 25 | 5 | 0 |  | 0 | 4-Transformation
TOTALS | 250 | 250 | 48 | 0 | 0 | 0 | All Phases
SECTION 2 — KPI IMPACT CALCULATION (WORKING CAPITAL & COST)
KPI Metric | Baseline | Current | Improvement | Annual Revenue ($) | $ Impact Formula | Quantified $ Benefit
DSO Reduction (days) | Enter Baseline DSO | Enter Current DSO | #VALUE! | Enter Annual Revenue $ | #VALUE! | #VALUE!
Cost of Capital (carrying cost %) | 0.06
DSO Working Capital Freed |  |  |  |  | #VALUE! | #VALUE!
Cash App Match Rate Gain (%) | Enter Baseline % | Enter Current % | #VALUE! | Enter Unmatched $ Volume | #VALUE! | #VALUE!
Write-off Rate Improvement (%) | Enter Baseline % | Enter Current % | #VALUE! | Enter Total AR Balance $ | #VALUE! | #VALUE!
Manual Hours Eliminated (hrs/wk) | Enter Baseline hrs | Enter Current hrs | #VALUE! | Enter Hourly Fully-Loaded Rate $ | #VALUE! | #VALUE!
Dispute Resolution Days Saved | Enter Baseline days | Enter Current days | #VALUE! | Enter Avg Dispute $ Value | #VALUE! | #VALUE!
TOTAL QUANTIFIED ANNUAL KPI IMPACT | [5 empty] | #VALUE!
SECTION 3 — RECOVERY INVESTMENT ESTIMATE & PAYBACK
Investment Item | Description / Notes | One-Time Cost ($) | Annual Recurring ($)
AI Workflow & Automation Build-Out | Prompt library, MCP configs, integration fees
Staff Training & Change Management | Training hours, LMS, external facilitator
Vendor Professional Services | Implementation support, optimization sprints
Internal Staff Time (IT + AR + Mgmt) | Hours × fully-loaded hourly rate
Software / Add-on Licenses | Any new modules or AI add-ons required
Contingency Reserve (10%) | 10% of items above — auto-calculated | 0 | 0
TOTAL INVESTMENT |  | 0 | 0
Net Annual Benefit (KPI Impact − Annual Recurring Cost) |  | #VALUE!
Payback Period (One-Time Investment ÷ Net Annual Benefit) — Months |  | —
ROI % (Net Annual Benefit ÷ One-Time Investment × 100) |  | —
SECTION 4 — EXECUTIVE SUMMARY (AUTO-POPULATED)
ℹ️ This section auto-populates from your data. Copy and paste into your CFO presentation or executive memo.
#VALUE!
LS Financial Management Group ¦ www.lsfinancialmanagement.com ¦ © 2026 ¦ CONFIDENTIAL — Licensed to purchaser only